## Sheet1
Badge Order Tracking
| Project: |  | BsidesKC 2022
Item Type | Description | QTY | Vendor | Price | Paid By | Tracking | Arrival Date | Received
PCB | Sponsor | 25 | PCBWay | 1409.25 | BP | 6599387992 | 2022-09-16
PCB | Badge Pirates | 25 | PCBWay | " | BP | " | "
PCB | Participant | 405 | PCBWay | " | BP | " | "
PCB | Volunteer | 40 | PCBWay | " | BP | " | "
PCB | Village | 30 | PCBWay | " | BP | " | "
PCB | Organizer | 15 | PCBWay | " | BP | " | "
PCB | Badge Pirates | 15 | PCBWay | " | BP | " | "
PCB | Sponsor SOA's, Speaker Add (10) | 50 | PCBWay | 315.05 | BP
PCB | Kids Badge | 50 | PCBWay | 203.51 | BP | 8977584943 | 2022-09-14
Components | Resistors, Capacitors, LED, CH340N, Button, Switch, Battery mgmt | - | LCSC | 1322.27 | Carl
Components | Voltage Regulators | 500 | LCSC | 178.59 | Carl | 2854852803 | 2022-09-12
Components | 14500 Batteries | 450 | eBay | 608.55 | Carl | 1Z9L0T7V0320016817 | 2022-09-16
Components | EC11 Rotary Encoders |  | Mouser | 1281.03 | Carl | 1Z7759450215446376
Components | ESP32-S2, LED's | 450 | Mouser | 3991.32 | Kevin | 1Z7759450315381425 | 2022-09-07 | 2022-09-07
Components | Kids Badge - IR TX/RX, Transisters | 100 | Mouser | 90.39 | Kevin | 1Z7759450315420785 | 2022-09-08 | 2022-09-08
PCB | Solder Village SAO, Poster SAO | 400+ | PCBWay | 293.7 | BP
Duty on PCB Boards | Duty on Main PCB Board Order | 1 | DHL | 313.13 | kevin |  | 2022-09-16 | 2022-09-16
Duty | Duty on LCSC Component Order | 1 | DHL | 380 | Carl |  | 2022-09-15 | 2022-09-15
Components | Rotary Knobs | 1 | AliExpress | 323.49 | Carl |  | 2022-09-20
|  |  |  | Carl Total | 4093.93